## Sprint Gantt
Sprint | Team | Output | Start Date | End Date | 27-Jul | 28-Jul | 29-Jul | 30-Jul | 31-Jul | 01-Aug | 02-Aug | 03-Aug | 04-Aug | 05-Aug | 06-Aug | 07-Aug | 08-Aug | 09-Aug | 10-Aug | 11-Aug | 12-Aug | 13-Aug | 14-Aug | 15-Aug | 16-Aug | 17-Aug | 18-Aug | 19-Aug | 20-Aug | 21-Aug | 22-Aug | 23-Aug | 24-Aug | 25-Aug | 26-Aug | 27-Aug | 28-Aug | 29-Aug | 30-Aug | 31-Aug | 01-Sep | 02-Sep | 03-Sep | 04-Sep | 05-Sep | 06-Sep | 07-Sep | 08-Sep | 09-Sep | 10-Sep | 11-Sep | 12-Sep | 13-Sep | 14-Sep | 15-Sep | 16-Sep | 17-Sep | 18-Sep | 19-Sep | 20-Sep | 21-Sep | 22-Sep | 23-Sep | 24-Sep | 25-Sep | 26-Sep | 27-Sep | 28-Sep | 29-Sep | 30-Sep | 01-Oct | 02-Oct | 03-Oct | 04-Oct | 05-Oct | 06-Oct | 07-Oct | 08-Oct | 09-Oct | 10-Oct | 11-Oct | 12-Oct | 13-Oct | 14-Oct | 15-Oct | 16-Oct
Sprint 1: Kickoff & Requirements | Data Team | Investigating requirements (data side); Iniitial scraping started Classify the scraping strategy for each companies and salary page | 2026-07-27 | 2026-08-06
| Web Team | Simple page UI built for comments/feedback; frontend demo for page visualisation | 2026-07-27 | 2026-08-06
| Whole Team — Review & Update | Sprint review held; requirements and backlog updated | 2026-08-07 | 2026-08-09
Sprint 2: Core Build | Data Team | Identify strategy to classify skills based on jd and skills (context, LLM, ..) Structure the data pipeline to integrate with backend for visualisation | 2026-08-10 | 2026-08-16
| Web Team | Landing page + search/filter UI being built | 2026-08-10 | 2026-08-16
| Whole Team — Review & Update | Sprint review held; Deliverable 1 finalized and submitted | 2026-08-17 | 2026-08-18
Sprint 3: Scraper Expansion & Data Modeling | Data Team | Scraper expanded beyond Sprint 1 prototype to more companies; data model refined for classification | 2026-08-19 | 2026-09-03
| Web Team | UI refinements based on early feedback | 2026-08-19 | 2026-09-03
| Whole Team — Review & Update | Sprint review held; scraper and data model updated | 2026-09-04 | 2026-09-08
Sprint 4: Data Pipeline | Data Team | Scraper scaled to all companies; LLM classification pipeline built | 2026-09-09 | 2026-09-19
| Web Team | Trend charts (skill demand, job volume) built on frontend | 2026-09-09 | 2026-09-19
| Whole Team — Review & Update | Sprint review held; pipeline and data model updated | 2026-09-20 | 2026-09-22
Sprint 5: Feature Finalization | Data Team | Data/classification features finalized | 2026-09-23 | 2026-09-27
| Web Team | UI/UX features finalized | 2026-09-23 | 2026-09-27
| Whole Team — Review & Update | Sprint review held; Deliverable 2 and Deliverable 3.1 submitted | 2026-09-28 | 2026-09-29
Sprint 6: Demo Prep | Data Team | Demo data/scenarios prepared | 2026-09-30 | 2026-10-04
| Web Team | Product demo recorded and edited | 2026-09-30 | 2026-10-04
| Whole Team — Review & Update | Sprint review held; Deliverable 3.2 demo video submitted | 2026-10-05 | 2026-10-06
Sprint 7: Final Delivery | Data Team | Backend/data pipeline deployed to production | 2026-10-07 | 2026-10-11
| Web Team | Frontend deployed to production; final report being drafted | 2026-10-07 | 2026-10-11
| Whole Team — Review & Update | Sprint review held; Final Report submitted; Showcase presented | 2026-10-12 | 2026-10-13
Wrap-up | Data Team | Data pipeline documentation finalized | 2026-10-14 | 2026-10-15
| Web Team | Website documentation finalized | 2026-10-14 | 2026-10-15
| Whole Team — Review & Update | Retrospective held; peer feedback submitted | 2026-10-16 | 2026-10-16

## Legend
Team | Color
Data Team
Web Team
Whole Team — Review & Update